## Sheet1
PROCUREMENT PLAN FOR NON-REIMBURSABLE TECHNICAL COOPERATIONS
Country: JAMAICA |  |  |  |  | Executing agency: The University Of The West Indies At Mona |  |  |  |  | Sector: Public
Project number: JA-T1169 |  |  |  |  | Title of Project: Blue carbon restoration in southern Clarendon, Jamaica
Period covered by the plan: 84 months
Threshold for ex-post review of procurements: |  |  |  | Goods and services (in US$): N/A |  |  | Consulting services(in US$): $2,450,000
Item Nº | Ref. AWP | Description (1) | Estimated contract cost (US$) | Procurement Method (2) | Review of procurement (3) | Source of financing and percentage |  | Estimated date of the procurement notice or start of the contract | Technical review by the PTL (4) | Comments
[6 empty] | IDB/MIF % | Local/ other % |  |  |  | Direct Contracting
|  | Component 1 | [8 empty] | International Competitive Bidding
|  | Consulting firm to determine site characteristics and the impact analysis | 100000 | QCBS |  | 100000 |  | Jan 1st 2020 | 2020-03-01 |  | Shopping
|  | Component 2 | [8 empty] | Least-Cost Selection
|  | Consulting firm - Formulation and implementation of actions and measures to restore mangrove ecosystems | 1310000 |  |  | 1310000 |  | June 20th 2020 | 2020-11-01 |  | Quality and Cost Based Selection
Component 3
|  | Consulting firm for the development of a sustainable charcoal production plan | 250000 |  |  | 250000 |  | April 3rd 2020 | July 1st 2020 |  | Quality Based Selection
Component 4
|  | Consulting firm for the management and monitoring of restoration program | 375000 |  |  | 375000 |  | Sept 1st 2020 | Jan 1st 2021 |  | Selection Based on the Consultants' Qualifications
|  | Component 5 | [8 empty] | Selection under a Fixed Budget
|  | Consulting services for knowledge dissemination and training | 90000 |  |  | 90000 |  | April 3rd 2020 | July 1st 2020 |  | Individual Consultant
|  | Project Administration | [8 empty] | National System
|  | Individual consultant for finance and accounting | 90000 |  |  | 90000 |  | Feb 20th 2020 | April 1st 2020
|  | Individual consultant - Procurement officer | 80000 |  |  | 80000 |  | Feb 20th 2020 | April 1st 2020
|  | Individual consultant - Wetland Ecologist | 80000 |  |  | 80000 |  | Feb 20th 2020 | April 1st 2020
|  | Auditing | 35000 |  |  | 35000 |  | Feb 1st 2026 | April 1st 2026
|  | Project Evaluation | 40000 |  |  | 40000 |  | Jan 1st 2023 | April 1st 2023
Total |  |  | 2450000 | Prepared by: Gerard Alleng |  |  | Date: November 2019
(1) Grouping together of similar procurement is recommended, such as computer hardware, publications, travel, etc. If there are a number of similar individual contracts to be executed at different times, they can be grouped together under a single heading, with an explanation in the comments column indicating the average individual amount and the period during which the contract would be executed. For example: an export promotion project that includes travel to participate in fairs would have an item called "airfare for fairs", an estimated total value od US$5,000, and an explanation in the Comments column: "This is for approximately four different airfares to participate in fairs in the region in years X and X1".
(2) Goods and works: CB: Competitive bidding; PC: Price comparison; DC: Direct contracting.
(2) Consulting firms: CQS: Selection Based on the Consultants' Qualifications; QCBS: Quality and cost-based selection; LCS: Least Cost Selection; FBS: Selection under a Fixed Budget; SSS: Single Source Selection; QBS: Quality Based selection.
(2) Individual consultants: IICQ: International Individual Consultant Selection Based on Qualifications; SSS: Single Source Selection.
(2) Country system: include selection Method
(3) Ex-ante/ex-post review: In general, depending on the institutional capacity and level of risk associated with the procurement, ex-post review is the standard modality. Ex-ante review can be specified for critical or complex process.
(4) Technical review: The PTL will use this column to define those procurement he/she considers "critical "or "complex "that require ex ante review of the terms of reference, technical specifications, reports, outputs, or other items.