## TCM Period 2019
|  | Operation Number: |  |  |  | JA-T1169 | [14 empty] | Inter-American Development Bank - IDB
|  | TCM Cycle: |  |  |  | TCM Period 2019
|  | Last Update: |  |  |  | 2019-12-06 16:25
Results Matrix
Outcomes
Outcome: | 1 An increase in coastal resilience and carbon storage, supporting improved ecosystem services in Jamaica
Indicators |  |  | Flags* |  | Unit of Measure |  |  | Baseline |  | Baseline Year |  | Means of verification |  |  | 2019 |  | 2020 |  | 2021 |  |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | EOP
1.1 Increased mangrove cover |  |  |  |  | Area (Hectares) |  |  | 0 |  | 2019 |  | Report |  | P | 0 |  | 10 |  | 100 |  |  | 500 |  | 990 |  | 0 |  | 0 |  | 1600
[14 empty] | P(a) | 0 |  | 10 |  | 100 |  |  | 500 |  | 900 |  | 0 |  | 0 |  | 1600
[14 empty] | A | 0 | [14 empty] | 1600
1.2 Number of private sector participants involved in mangrove restoration |  |  |  |  | # |  |  | 0 |  | 2019 |  | Project report |  | P | 0 |  | 4 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 4
[14 empty] | P(a) | 0 |  | 4 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 4
[14 empty] | A | 0
Outputs: Annual Physical and Financial Progress
1 Site characteristics and impact analysis. | [15 empty] | Physical Progress | [16 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2019 |  | 2020 |  |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 | EOP |  | 2019 | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | EOP |  |  | Theme | Fund | Flags
1.1 Feasibility study completed |  |  |  | Assessment of site characteristics and impact analysis |  |  | Studies (#) |  | 0 |  | 2019 |  | Project report |  |  | P |  | 0 |  | 1 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P | 0 | 30000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 30000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 1 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P(a) | 0 | 30000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 30000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
1.2 Environmental impact assessment completed |  |  |  | Analysis of the impacts of the restoration activities on the ecosystem |  |  | Assessments (#) |  | 0 |  | 2020 |  | Assessment reports |  |  | P |  | 0 |  | 3 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | P | 0 | 70000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 70000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 3 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | P(a) | 0 | 70000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 70000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
2 Formulation and implementation of actions and measures to restore 1,600 ha of mangroves | [15 empty] | Physical Progress | [16 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2019 |  | 2020 |  |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 | EOP |  | 2019 | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | EOP |  |  | Theme | Fund | Flags
2.1 Action plans designed |  |  |  | Formulation of action plans for restoration |  |  | Action Plans (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 2 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | P | 0 | 80000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 80000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 2 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | P(a) | 0 | 80000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 80000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
2.2 Action plans implemented |  |  |  | Implementation of restoration plans for degraded areas |  |  | Action Plans (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 1 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | P | 0 | 90000 |  |  | 640000 |  |  | 475000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1205000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 1 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | P(a) | 0 | 90000 |  |  | 640000 |  |  | 475000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 1205000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
2.3 Training workshops delivered |  |  |  | Training workshops for private sector actors involved in mangrove conservation |  |  | Workshops (#) | [8 empty] | P |  | 0 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 | 4 | P | 0 | 10000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 0 |  |  | 0 |  |  | 25000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 1 |  |  | 1 |  | 1 |  | 1 |  | 0 |  | 0 | 4 | P(a) | 0 | 10000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 0 |  |  | 0 |  |  | 25000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
3 Development of a sustainable charcoal production program | [15 empty] | Physical Progress | [16 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2019 |  | 2020 |  |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 | EOP |  | 2019 | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | EOP |  |  | Theme | Fund | Flags
3.1 Awareness raising campaigns designed/implemented |  |  |  | Stakeholder/community engagement in sustainability program on mangrove restoration |  |  | Campaigns (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 1 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P | 0 | 20000 |  |  | 20000 |  |  | 35000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 75000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 1 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P(a) | 0 | 20000 |  |  | 20000 |  |  | 35000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 75000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
3.2 Action plans designed |  |  |  | Development of a sustainable charcoal production plan |  |  | Action Plans (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 0 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P | 0 | 100000 |  |  | 75000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 175000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P(a) | 0 | 100000 |  |  | 75000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 175000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
4 Management and monitoring of restoration program | [15 empty] | Physical Progress | [16 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2019 |  | 2020 |  |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 | EOP |  | 2019 | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | EOP |  |  | Theme | Fund | Flags
4.1 Monitoring and Evaluation Plan developed |  |  |  | Development of M&E plan |  |  | Plans (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 0 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P | 0 | 0 |  |  | 80000 |  |  | 40000 |  |  | 100000 |  |  | 40000 |  |  | 40000 |  |  | 300000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | P(a) | 0 | 0 |  |  | 80000 |  |  | 40000 |  |  | 100000 |  |  | 40000 |  |  | 40000 |  |  | 300000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
4.2 Diagnostics and assessments completed |  |  |  | Analysis of improvement of economic value of rehabilitated areas |  |  | Diagnostics (#) |  | 0 |  | 2020 |  | Assessment reports |  |  | P |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 | 1 | P | 0 | 75000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 75000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 1 |  | 0 | 1 | P(a) | 0 | 75000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 75000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
5 Knowledge dissemination and training | [15 empty] | Physical Progress | [16 empty] | Financial Progress
Outputs |  |  |  | Output Description |  |  | Unit of Measure |  | Baseline |  | Baseline Year |  | Means of verification |  |  |  |  | 2019 |  | 2020 |  |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 | EOP |  | 2019 | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | EOP |  |  | Theme | Fund | Flags
5.1 Technical notes created |  |  |  | Technical and research papers produced |  |  | Notes (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 1 |  | 1 |  | 2 | 4 | P | 0 | 0 |  |  | 0 |  |  | 10000 |  |  | 0 |  |  | 0 |  |  | 10000 |  |  | 20000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 |  | 0 |  | 1 |  | 1 |  | 2 | 4 | P(a) | 0 | 0 |  |  | 0 |  |  | 10000 |  |  | 0 |  |  | 0 |  |  | 10000 |  |  | 20000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
5.2 Individuals Trained |  |  |  | Persons trained from surrounding communities on mangrove ecosystems and ecosystem services: 50% are to be women |  |  | Individuals (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 5 |  |  | 30 |  | 20 |  | 20 |  | 0 |  | 0 | 75 | P | 0 | 0 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 0 |  |  | 0 |  |  | 30000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 5 |  |  | 30 |  | 20 |  | 20 |  | 0 |  | 0 | 75 | P(a) | 0 | 0 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  | 0 |  |  | 0 |  |  | 30000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
5.3 Virtual platforms designed |  |  |  | Knowledge platform developed for the dissemination and sharing of the results of the project |  |  | Platforms (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 0 |  |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 | 1 | P | 0 | 0 |  |  | 0 |  |  | 10000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 10000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 0 |  | 1 |  | 0 |  | 0 |  | 0 | 1 | P(a) | 0 | 0 |  |  | 0 |  |  | 10000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 10000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
5.4 Workshops organized |  |  |  | Workshops/seminars/conferences undertaken to showcase project and results of interventions |  |  | Workshops (#) |  | 0 |  | 2020 |  | Project report |  |  | P |  | 0 |  | 0 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 5 | P | 0 | 0 |  |  | 10000 |  |  | 0 |  |  | 10000 |  |  | 10000 |  |  | 0 |  |  | 30000 |  |  | Biodiversity and Ecosystem Conservation | BLU
[16 empty] | P(a) |  | 0 |  | 0 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 5 | P(a) | 0 | 0 |  |  | 10000 |  |  | 0 |  |  | 10000 |  |  | 10000 |  |  | 0 |  |  | 30000
[16 empty] | A |  | 0 | [13 empty] | 0 | A | 0 | [18 empty] | 0
Other Cost | [33 empty] | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | Cost
[33 empty] | P |  |  |  | 60000 |  |  | 45000 |  |  | 70000 |  |  | 40000 |  |  | 40000 |  |  | 70000 |  |  | 325000
Project Implementation Unit (consultants for accounting, procurement, wetlands, audits and evaluations)
[33 empty] | P(a) |  |  |  | 60000 |  |  | 45000 |  |  | 70000 |  |  | 40000 |  |  | 40000 |  |  | 70000 |  |  | 325000
A
Total Cost | [33 empty] | 2019 |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | Total Cost
[33 empty] | P |  |  | 535000 |  |  | 885000 |  |  | 655000 |  |  | 165000 |  |  | 90000 |  |  | 120000 |  |  | 2450000
[33 empty] | P(a) |  |  | 535000 |  |  | 885000 |  |  | 655000 |  |  | 165000 |  |  | 90000 |  |  | 120000 |  |  | 2450000
A